## Agile Project Plan - BLANK
Simplilearn Capstone Project #4 - ICIN Bank
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | ICIN Bank with all the required functionalities
| ICIN Bank | Harshad Kalantri | 2021-05-12 | 2021-06-03 |  | 95% |  | SCOPE STATEMENT | The final phase project of FSD in Java using the technologies for a Web Application.
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 | Backend | Harshad Kalantri | 4 | 12th May | 19th May | 8 Days | Completed | SpringBoot Application is Developed.
| Feature 1 | Controller - Creating Accounts | Harshad Kalantri | 2 | 13th May | 19th May | 6 Days | Completed | All Controllers are developed and tested/debugged
| Feature 2 | Implementation and Services | Harshad Kalantri | 1 | 14th May | 19th May | 6 Days | Completed | Controller alongside databases and entities are completed.
| Feature 3 | Debugging and Errors | Harshad Kalantri | 1 | 18th May | 20th May | 3 Days | Completed | All tests for creating any issues have been resolved.
| Sprint 2 | Frontend | Harshad Kalantri | 5 | 16th May | 27th May | 11 Days | Completed | Angular 10.0.5 CLI development and deployment is successful.
| Feature 4 | Creating Project, Components and Services | Harshad Kalantri | 2 | 16th May | 19th May | 4 Days | Completed | Deploying the Angular App and creating the necessary components and services wrt Backend
| Feature 5 | Implementing Frontend Features | Harshad Kalantri | 2 | 20th May | 24th May | 5 Days | Completed | Creating and editing the code in Angular wrt Admin, User and common code functionalities.
| Feature 6 | Resolving Issues with Integration | Harshad Kalantri | 1 | 24th May | 27th May | 2 Days | Completed | Resolving CORS Issues, Account and Transaction issues, Database Integration, etc.
| Sprint 3 | Testing and Deployment | Harshad Kalantri | 5 | 29th May | 3rd June | 6 Days | Nearly Completed | Selenium Testing(Automated) and AWS EC2 Deployment
| Feature 7 | Selenium Testing | Harshad Kalantri | 2 | 29th May | 31st May | 3 Days | Completed | Selenium Testing of 3 Modules - AdminLogin, ChequebookRequest and User Registration - Successful.
| Feature 8 | Resolving Issues with Frontend and Backend | Harshad Kalantri | 1 | 30th May | 2nd June | 3 Days | Completed | Issues with function-calling and Output response - still some issues but resolved majorly
| Feature 9 | AWS Deployment | Harshad Kalantri | 1 | 3rd June | 3rd June | 1 Day | Completed | AWS EC2, RDS and S3 Bucket were used to deploy the app.
| Feature 10 | Jenkins CI/CD pipeline | Harshad Kalantri | 1 | 3rd June | 4th June | 1 Day | Not Completed | Issues with laptop, jenkins usage.
| Features/Sprint | Estimated Burndown | Actual Burndown
| 1 | 100 | 96
| 2 | 88 | 88
| 3 | 77 | 80
| 4 | 71 | 70
| 5 | 60 | 65
| 6 | 52 | 55
| 7 | 40 | 43
| 8 | 33 | 36
| 9 | 20 | 25
| 10 | 9 | 12
| 11 | 0 | 3